## 30-Day Plan
Day | Date | Phase | Topic | What to do | Time | Status | Output / checkpoint
1 | 2026-09-29 | Foundation | LLM API foundations | Review chat/completions, system prompts, tokens, context windows, temperature; build one clean Python LLM script. | 2–3h | Completed | Working LLM script
2 | 2026-09-30 | Foundation | Structured outputs | Learn Pydantic/JSON structured output; make an LLM return a validated TravelPlan object. | 2–3h | Completed | Validated JSON/Pydantic output
3 | 2026-10-01 | Foundation | Tool calling | Learn function/tool calling; build calculator + weather/mock-search tools. | 2–3h | Completed | 3 working tools
4 | 2026-10-02 | Foundation | Tool calling mini project | Mini Project 1: build a small Tool-Using Travel Assistant with 3 tools and error handling. | 3–4h | Completed | Mini Project 1 completed
5 | 2026-10-03 | Foundation | FastAPI basics | Learn REST, endpoints, request/response models, env vars; expose your assistant through FastAPI. | 2–3h | Completed | FastAPI endpoint
6 | 2026-10-04 | RAG | Embeddings | Understand embeddings, cosine similarity, semantic search; experiment with a small text dataset. | 2–3h | Completed | Embedding similarity demo
7 | 2026-10-05 | RAG | Vector search | Learn FAISS; index documents and retrieve top-k chunks. Understand metadata/chunking basics. | 2–3h | Completed | FAISS retrieval demo
8 | 2026-10-06 | RAG | RAG pipeline | Build PDF/text → chunk → embed → retrieve → LLM answer pipeline. | 3h | Completed | Working RAG
9 | 2026-10-07 | RAG | RAG quality | Learn chunk size/overlap, top-k, citations, hallucination/grounding; improve your RAG app. | 2–3h | Completed | Improved grounded answers
10 | 2026-10-08 | RAG | RAG mini project | Mini Project 2: build a College/Company Knowledge Assistant with citations. | 3–4h | Not Started | Mini Project 2 completed
11 | 2026-10-09 | Agents | Agent concepts | Learn workflow vs agent, ReAct, state, planning, routing, retries, human approval. | 2–3h | Not Started | Agent architecture notes
12 | 2026-10-10 | Agents | LangChain essentials | Learn prompts, models, tools, retrievers and structured output in LangChain; reproduce one earlier app. | 2–3h | Not Started | LangChain prototype
13 | 2026-10-11 | Agents | LangGraph basics | Learn StateGraph, nodes, edges, conditional routing, state and checkpoints. | 3h | Not Started | LangGraph graph
14 | 2026-10-12 | Agents | Build first agent | Create a research agent: plan → search/tool → summarize → verify → answer. | 3–4h | Not Started | Research agent
15 | 2026-10-13 | Agents | Agent memory/state | Add conversation state and persistent user preferences; understand when memory should/shouldn't be used. | 2–3h | Not Started | State/memory working
16 | 2026-10-14 | Agents | Agent reliability | Add retries, tool errors, max steps, fallbacks and human approval for risky actions. | 2–3h | Not Started | Reliable agent with limits
17 | 2026-10-15 | Modern AI | MCP fundamentals | Learn what MCP solves; understand client/server, tools, resources and prompts; run a simple MCP server. | 2–3h | Not Started | MCP concepts + server
18 | 2026-10-16 | Modern AI | MCP + agent | Connect one MCP tool/server to your agent and compare MCP tools with ordinary function calling. | 2–3h | Not Started | Agent using MCP
19 | 2026-10-17 | Production | PostgreSQL | Learn practical PostgreSQL: tables, joins, indexes, JSONB; connect with Python. | 2–3h | Not Started | PostgreSQL app DB
20 | 2026-10-18 | Production | pgvector | Learn vector storage/search with pgvector; understand when PostgreSQL can replace a separate vector DB. | 2–3h | Not Started | pgvector search
21 | 2026-10-19 | Production | Evaluation | Learn basic eval datasets, relevance, faithfulness/grounding, tool success, latency and cost. | 2–3h | Not Started | Eval checklist
22 | 2026-10-20 | Production | Evaluation implementation | Add 10–20 test cases to your RAG/agent app; record pass/fail, latency and obvious hallucinations. | 2–3h | Not Started | 10–20 eval cases
23 | 2026-10-21 | Production | Security | Learn prompt injection, data leakage, excessive tool permissions, secrets and basic auth/rate limiting. | 2h | Not Started | Security checklist
24 | 2026-10-22 | Production | Docker + deployment | Learn Dockerfile, compose basics, env vars; containerize your FastAPI AI app. | 3h | Not Started | Dockerized app
25 | 2026-10-23 | Big Project | Project architecture | Big Project Day 1: choose/build 'AI Research & Planning Agent'; architecture, repo, DB schema, API design. | 4–5h | Not Started | Big project architecture
26 | 2026-10-24 | Big Project | RAG + knowledge | Big Project Day 2: document ingestion, chunking, embeddings, pgvector/FAISS retrieval, citations. | 4–5h | Not Started | RAG module
27 | 2026-10-25 | Big Project | Agent + tools | Big Project Day 3: LangGraph agent with search, calculator, database tools; state + routing. | 4–5h | Not Started | Agent + tools
28 | 2026-10-26 | Big Project | Reliability + UI/API | Big Project Day 4: FastAPI, structured outputs, retries, guardrails, logging, evaluation tests; simple frontend/Swagger demo. | 4–5h | Not Started | API + evaluation + guardrails
29 | 2026-10-27 | Big Project | Deploy + portfolio | Big Project Day 5: Docker/deploy, README, architecture diagram, demo video/screenshots, resume/GitHub documentation. | 4–5h | Not Started | Deployed/documented project
30 | 2026-10-28 | Revision | Final review | Review weak areas; clean GitHub; write what you learned and prepare interview questions/explanations for every component. | 2–3h | Not Started | Portfolio + interview revision

## Skill Map
Area | Must know by end of month | Depth target | Priority
LLM APIs | API calls, context, streaming, structured output | Practical | High
Tool calling | Schemas, tool selection, results, errors | Practical | High
RAG | Chunking, embeddings, retrieval, citations | Strong practical | Very High
Vector DB | FAISS + basic pgvector | Practical | High
Agents | Workflow vs agent, state, planning, routing | Strong practical | Very High
LangGraph | Nodes, edges, state, conditional routing | Practical | Very High
LangChain | Core components; use without hiding fundamentals | Working knowledge | Medium
MCP | Client/server, tools/resources/prompts | Working knowledge | Medium
FastAPI | REST endpoints, Pydantic, env vars | Practical | High
PostgreSQL | CRUD, joins, indexes, JSONB | Working knowledge | Medium
Evaluation | Test set, relevance, groundedness, latency/cost | Practical | High
Security | Prompt injection, secrets, permissions | Working knowledge | High
Docker | Dockerfile, compose basics, env vars | Working knowledge | Medium
Git/GitHub | Branches, commits, README, portfolio | Practical | High

## Projects
Project | Goal | Required features | Tech | Portfolio value
Mini Project 1 | Tool-Using Travel Assistant | 3 tools, tool calling, structured output, error handling | Python + LLM API | Shows function/tool calling
Mini Project 2 | Knowledge Assistant | PDF ingestion, chunking, embeddings, vector search, citations | Python + FAISS + LLM | Shows RAG
Big Project | AI Research & Planning Agent | RAG + LangGraph + tools + PostgreSQL/pgvector + FastAPI + eval + guardrails + Docker | Python + LangGraph + FastAPI + PostgreSQL | Main GenAI/Agentic AI portfolio project